## Front_Sheet
SuRF-UK Framework for Assessing the Sustainability of Soil and Groundwater Remediation Tier 1 Sustainability Assessment Spreadsheet Tool
This spreadsheet has been developed by AECOM in collaboration with the SuRF UK Steering Group, and provides a standardised record for the completion of a Tier 1 qualitative sustainable remediation assessment in accordance with the updated SuRF UK guidance (Supplementary Reports SR1 and SR2 published in 2020 and available at https://www.claire.co.uk/projects-and-initiatives/surf-uk). The spreadsheet has been developed and provided freely for use in support of the SuRF UK guidance, and this guidance should be read in conjunction with the use of this spreadsheet. Acknowledgements Kevin Shepherd, Emily Ghedia and Simon Cole (AECOM) SuRF UK Steering Group (https://www.claire.co.uk/projects-and-initiatives/surf-uk/79-surf-uk-steering-group) Disclaimer The authors, contributors, and funders will not be responsible for any loss, however arising, from the use of, or reliance on, this spreadsheet, nor do they assume responsibility or liability for errors or omissions. Users are advised to confirm the adequacy of the spreadsheet for the intended use and to take appropriate professional advice where necessary.

## Introduction
Tier 1 Sustainability Assessment
This spreadsheet should be used to document your progress through the Tier 1 qualitative sustainability assessment. It is based on the SuRF-UK briefcase and should enable assessments to be carried out systematically according to SuRF-UK's guidance (Supplementary Report 1 of the SuRF-UK Framework: A general approach to sustainability assessment for use in achieving sustainable remediation, 2nd Edition). The process is divided into three tasks: - Task 1: Preparation - describing the project, the purpose of the assessment, the stakeholders, the constraints and the reporting/dialogue plan - Task 2: Definition - defining the objectives, boundaries, scope, methodology and uncertainties - Task 3: Execution - tables to aid the execution of the assessment, including the SuRF-UK assessment indicators The preparation and definition tasks provide the “framing” of the sustainability assessment.
Document Guide
Task 1: Preparation
Prep1_Decision&Stakeholders | This describes the decision the sustainability assessment has to support and the stakeholders
Prep2_TheProject | This describes the project, including the project goals and the remedial options to be considered
Prep3_Constraints&Opportunities | This sets out the constraints and opportunities of the project
Prep4_Reporting&Dialogue | This describes how reporting and dialogue will involve the stakeholders identified in Step 1
Task 2: Definition
Defn1&2_Objectives&Boundaries | This summarises the preparatory work and identifies the boundary conditions
Defn3_Scope | This sets out the scope of the assessment and the criteria to be scored
Defn4_Methodology | This sets out the method by which the options will be compared
Defn5_Uncertainty | This sets out how uncertainties will be identified and addressed
Defn6_Sensitivity | This sets out how the sensitivity of the assessment to criteria and assumptions will be addressed
Task 3: Execution
Excecution_Supporting | This is available for storing supporting information during the assessment process
Execution_Assessment | This contains the assessment table
Task 3: Execution - Sensitivity Analysis
Sensitivity_Supporting | This is available for storing supporting information during the sensitivity analysis
Sensitivity_Assessment | This contains the sensitivity analysis table
Key:
Guidance text for the use of this document is highlighted by green shading

## Prep1_Decision&Stakeholders
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Preparation - Step 1: Enter assessment details
Table P1a - Assessment details
Project Name
Project Number
Assessment Completed by
Date of Assessment
Preparation - Step 1: Describe the decision requirement
Describe the decision the sustainability assessment is intended to support and how its outcomes will be used, and also the stakeholders who need to be engaged with it.
Table P1b - The function of the assessment
The Sustainability Assessment can be used for different functions: a) Stage A: For a project or land use planning and design stage with consideration of different land uses or remediation strategies; and/or, b) Stage B: When the land use or remediation strategy is already confirmed and the focus is on the selection and implementation of the remediation system.
Consideration |  | Answer
To what extent does this assessment cover Stage A?
To what extent does this assessment cover Stage B?
Table P1c - The decisions to be made
List the decisions/actions that are expected to be supported by the sustainability assessment and describe how it is linked to the wider project management scheme:
Decisions/Actions |  | How does this link to the wider project management scheme?
Table P1d - The stakeholders involved
List the “dialogue partners” and their roles: - Users of the sustainability assessment (e.g. client, consultant, regulator, planner etc.) - Other parties who will need to play an active role in the sustainability assessment (e.g. the planner asks for some form of community input).
User/Other active party | Dialogue Partner |  | Role
Table P1e - The wider audience
List the “wider audience” (if any) for the sustainability assessment, who will be told about the findings but will not play an active role in the assessment process.
List of wider audience members
Return to Introduction

## Prep2_TheProject
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Preparation - Step 2: Describe the project
Clearly describe the project’s remediation, risk management goals and any wider goals of importance. Specify the options to be compared using sustainability assessment.
Table P2a - Project goals
List and clearly describe the project goals in as much detail as possible.
Project Goals
Table P2b - Options for delivering the project
List and clearly describe the options for delivering the project that are to be compared using sustainability assessment.
Option | Option Goal | Option Name | Description
Return to Introduction

## Prep3_Constraints&Opportunities
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Preparation - Step 3: Describe constraints and opportunities
Identify constraints and opportunities. Constraints limit possibilities for remediation. Opportunities are where features of the site could create benefits, for examples synergies in energy or materials use.
Constraints limit what options are feasible, and may set minimum thresholds that have to be achieved for different sustainability considerations. Examples include: - Available time, space and budget - Decisions that have already been taken and will not be revisited, for example, on-going / future land-use - Constraints resulting from regulations and policy (government or corporate) Opportunities for sustainability gain may favour particular remediation approaches, for example, integrating energy recovery with site restoration, or possible synergies such as linking to ground stabilisation for construction purposes.
Table P3a - Project constraints
Tabulate the key constraints and any consequential thresholds for them.
Constraint | Constraint Description | Threshold (if applicable)
Table P3b - Project opportunities
Tabulate the key opportunities and any consequential thresholds for them.
Opportunity | Opportunity Description | Threshold (if applicable)
Return to Introduction

## Prep4_Reporting&Dialogue
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Preparation - Step 4: Consider reporting and dialogue
Plan how reporting and dialogue will involve the stakeholders identified in Preparation - Step 1, in line with the SuRF-UK Framework’s Key Principles, specifying who will be involved and when.
Plan how reporting and dialogue will be undertaken, specifying who will be involved and when: - Who will be involved as dialogue partners or as the wider audience for dissemination? - When will they be involved - e.g. in the preparation and definition stages, or after a first iteration of a sustainability assessment by a ‘core’ team? - How they will be involved - e.g. collecting and using inputs, or resolving conflicting views? Reporting should be in line with the SuRF-UK Framework key principles so that remediation decisions, including the assumptions and supporting data used to reach them, are documented in a clear and easily understood format to demonstrate to interested parties that a sustainable (or otherwise) solution has been adopted.
Table P4a - Reporting and dialogue
Plan how reporting and dialogue will be undertaken, specifying who will be involved and when.
Who will be involved | Dialogue partner/Wider audience | When they will be involved | How they will be involved
Table P4b - Communication of results
Describe how the results will be communicated during the project and for the final reporting.
Return to Introduction

## Defn1&2_Objectives&Boundaries
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Definition - Step 1: Summarise objectives
Summarise the preparatory work carried out in the previous worksheets in the space below:
1) Which part of the decision making process is this assessment supporting (Stage A and/or Stage B)? Provide the reasoning.
2) Summarise the function of the sustainability assessment.
3) Summarise the project goals and options being considered.
4) Summarise the constraints and opportunities affecting the choices and the associated thresholds.
5) Summarise the plan for reporting and dialogue.
Definition - Step 2: Identify boundary conditions
Describe the assessment boundary conditions related to system, depth of consideration, proximity and timeframe.
Boundary conditions determine which effects will be considered within a sustainability assessment to ensure a fair, like-for-like comparison of options, they rationalise the use of effort, and usefully distinguish effects.
Table D2 - Boundary conditions
Complete the table with the boundary conditions for each factor listed.
Boundary Aspect | Inclusions/Exclusions
System
Life cycle
Temporal
Spatial
Definitions: System (that reflects all options equally); “Lifecycle” (e.g. dealing with equipment that will be re-used); Spatial (e.g. to distinguish local from global effects); Temporal (e.g. to distinguish temporary from permanent effects).
Return to Introduction

## Defn3_Scope
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Definition - Step 3: Agree scope / indicators
1) Describe the range of individual sustainability considerations included in the assessment.
2) Describe the level of detail.
3) Describe how criteria were included / excluded.
Table D3 - Assessment criteria
Detail the assessment criteria to be used and the way they will be scored.
Assessment criteria* | Included / excluded | Justification for inclusion / exclusion | Sub-indicators of specific relevance# | Level of confidence in data used for justification (if applicable) | Lines of evidence to be used to compare criteria between options | Priority for stakeholders
Environmental
Emissions to air
Soil and ground conditions
Groundwater and surface water
Ecology
Natural resources and waste
Social
Human health and safety
Ethics and equity
Neighbourhoods and locality
Communities and community involvement
Uncertainty and evidence
Economic
Direct economic costs and benefits
Indirect economic costs and benefits
Employment and employment capital
Induced economic costs and benefits
Project lifespan and flexibility
*: Assessment criteria are based on the SuRF-UK Headline Categories for Sustainability Indicators.
#: Identify any specific sub-indicators used to define and assess the headline indicators in the assessment (refer to Appendix 1 to SR2).
Return to Introduction

## Defn4_Methodology
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Definition - Step 4: Agree methodology
1) Define / agree the methodology by which options are going to be compared for the different sustainability criteria being considered. i.e. how those individual comparisons will be aggregated into broader assessment of sustainability; and how the assessment outcomes will be presented, interpreted and communicated.
Table D4 - Methodology
Summarise the methodology by which options will be compared for the criteria included in the assessment.
Assessment criteria* |  | Summary of Methodology
Environmental
Emissions to air
Soil and ground conditions
Groundwater and surface water
Ecology
Natural resources and waste
Social
Human health and safety
Ethics and equity
Neighbourhoods and locality
Communities and community involvement
Uncertainty and evidence
Economic
Direct economic costs and benefits
Indirect economic costs and benefits
Employment and employment capital
Induced economic costs and benefits
Project lifespan and flexibility
*: Assessment criteria are based on the SuRF-UK Headline Categories for Sustainability Indicators.
2) Define the tier of the assessment.
3) Decide upon the type of comparative approach you are going to use (tick the chosen option (✓). Note: Comparisons should be made on a criterion by criterion basis to ensure exhaustive consideration of sustainability effects and avoid unintentional confusion of effects.
Method 1 | Ranking options by comparing across a range of available options
Method 2 | Ranking by comparing against a baseline performance criterion on an option by option basis
Method 3 | Ranking by pair-wise comparison
Return to Introduction

## Defn5_Uncertainty
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Definition - Step 5: Agree how to deal with uncertainty
Set out an approach for identifying uncertainties and reviewing their potential effect on sustainability assessment outcomes.
At Tier 1 there are likely two broad causes of uncertainty: - Disagreement or uncertainty over what should be considered within the definition of the sustainability assessment (objectives, options, boundaries or scope) – definitional, - Insufficient or conflicting information describing individual sustainability criteria / indicators – informational. Uncertainties may emerge during an assessors work or as a result of the dialogue process.
Table D5 - Uncertainties
Describe the approach for identifying uncertainties.
Definitional Uncertainty | Informational Uncertainty | Extent of Informational Uncertainty
Return to Introduction

## Defn6_Sensitivity
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Definition - Step 6: Agree how to use sensitivity analysis
Describe how to use sensitivity analysis to analyse the impact of uncertainty on the outcome of the sustainability assessment.
A convenient means of assessing the impact of uncertainty on outcome is to use sensitivity analysis: - Comparing the outcome for sustainability assessment scenarios reflecting different definitions, and/or - Comparing the outcome for sustainability assessment scenarios reflecting the possible extremes in the range for a criterion based on available information and opinions. This could comprise a best and worst case scenario for different informational uncertainties, or the inclusion or exclusion of particular individual criteria that are contentious for some of the stakeholders. For example, sensitivity analysis scenarios could be included to consider uncertainty regarding future use of the site or extent of the contamination present. The outcomes of the sustainability assessment can then be compared for the different scenarios, for example outcomes of the ranking of approaches in a qualitative assessment.
Table D6 - Sensitivity Analysis
Describe the scenarios to be assessed by the sensitivity analysis.
Sensitivity Analysis Scenario | What is to be Changed for Analysis of this Scenario
Return to Introduction

## Execution_Supporting
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Execution - Supporting Table
Use this sheet to record specific information that provides the lines of evidence to support the comparisons being made, in terms of how well each Option performs according to the listed criteria. Also record any informational uncertainties that may affect comparison outcomes, how these were managed in the comparison, and if they need to go forward to a sensitivity analysis. Such information may be qualitative, semi-quantitative or quantitative in nature depending upon how much is known at the time. If more detail is required it may be useful to list the relevant indicators for each of the 15 listed criteria as separate rows, where these may cover several items, for example in the case of ENV5 Natural Resources and Waste, if there are several resources and waste streams to consider (e.g. water, land, energy/fuels, aggregates, recycled materials etc.).
Table E1 - Supporting Information
SuRF ref. | Assessment Criteria* | Information | Option 1 | Option 2 | Option 3 | Option 4 | Option 5
Environmental
ENV1 | Emissions to air | Lines of Evidence
Uncertainties
ENV2 | Soil and ground conditions | Lines of Evidence
Uncertainties
ENV3 | Groundwater and surface water | Lines of Evidence
Uncertainties
ENV4 | Ecology | Lines of Evidence
Uncertainties
ENV5 | Natural resources and waste | Lines of Evidence
Uncertainties
Social
SOC1 | Human health and safety | Lines of Evidence
Uncertainties
SOC2 | Ethics and equity | Lines of Evidence
Uncertainties
SOC3 | Neighbourhoods and locality | Lines of Evidence
Uncertainties
SOC4 | Communities and community involvement | Lines of Evidence
Uncertainties
SOC5 | Uncertainty and evidence | Lines of Evidence
Uncertainties
Economic
ECON1 | Direct economic costs and benefits | Lines of Evidence
Uncertainties
ECON2 | Indirect economic costs and benefits | Lines of Evidence
Uncertainties
ECON3 | Employment and employment capital | Lines of Evidence
Uncertainties
ECON4 | Induced economic costs and benefits | Lines of Evidence
Uncertainties
ECON5 | Project lifespan and flexibility | Lines of Evidence
Uncertainties
*: Assessment criteria are based on the SuRF-UK Headline Categories for Sustainability Indicators.
Return to Introduction

## Execution_Assessment
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Execution - Assessment Table
Use this sheet to record the outcome of the assessment by indicating the relative performance of each Option in terms of each criterion in the relevant cell. The assessment can be descriptive e.g. Poor, Fair, Good, colour coded or numerically ranked from relatively poor to relatively very good against the rest (refer to Definition - Step 4: Agree methodology). Summarise the justification of scores by reference to the key issues identified in Table E1 - Supporting Information. Record the inherent uncertainties in making the assessment and describe the degree of uncertainty associated with assessment against each criterion (Refer to Definition - Step 5: Agree how to deal with uncertainty). Note: Table E1 and Table E2 do not provide specific sections for aggregation of assessment criteria as this will depend upon the scope of assessment and selected methodology.
Table E2 - Assessment
Assessment Criteria | Remediation Options for Assessment |  |  |  |  | Summary of Justification of Scores (refer to Table E1 for more detail) | Uncertainty Arising (Description) | Uncertainty Arising (Extent)
| Option 1 | Option 2 | Option 3 | Option 4 | Option 5
Environmental
Emissions to air
Soil and ground conditions
Groundwater and surface water
Ecology
Natural resources and waste
Social
Human health and safety
Ethics and equity
Neighbourhoods and locality
Communities and community involvement
Uncertainty and evidence
Economic
Direct economic costs and benefits
Indirect economic costs and benefits
Employment and employment capital
Induced economic costs and benefits
Project lifespan and flexibility
Preferred option (tick)#
Environmental
Social
Economic
Overall
Justification for choice:
Requirement for Tier 2 assessment*
#: Refer to SR2 for guidance on how to visualise and report the results of the assessment
*: If a preferred option is not clear from Table E2
Return to Introduction

## Sensitivity_Supporting
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Execution - Supporting Table (Sensitivity Analysis)
Use this sheet to record specific information to describe the variation in assessment criteria for sensitivity analysis for the Scenarios listed in Table D6 - Sensitivity Analysis. Describe how the criteria have been changed for each Option for the sensitivity analysis of that Scenario. For example, has a best and a worst case scenario been applied to account for different informational uncertainties in a specific criterion identified in Table E1? Alternatively, has a particular individual criterion that is contentious for some of the stakeholders been excluded or included in the sensitivity analysis of the scenario? For example, ‘what if we consider particulate emissions’ on air quality to ‘what if we don’t’?
Table E3 - Sensitivity Analysis Supporting Information
Sensitivity Analysis Scenario | Assessment Criteria Changed | Option 1 | Option 2 | Option 3 | Option 4 | Option 5
*: Assessment criteria are based on the SuRF-UK Headline Categories for Sustainability Indicators.
Return to Introduction

## Sensitivity_Assessment
Project Name:
Project Number:
Assessment Completed by:
Date of Assessment:
Execution - Assessment Table (Sensitivity Analysis)
Use this sheet to record the outcome of the sensitivity analysis for the scenarios listed in Table D6 - Sensitivity Analysis. Replicate the Execution Assessment in Table E1, taking into account the adjustments described in Table E3 - Sensitivity Analysis Supporting Information for each Option. Indicate the relative performance of each Option in terms of each criterion in the relevant cell. The assessment methodology should be the same as that used in Table E2. Summarise the justification of the revised scores by reference to the key issues or differences identified in Table E1 - Supporting Information and Table E3 - Sensitivity Analysis Supporting Information. This table, E4 - Execution - Assessment Table (Sensitivity Analysis) can be replicated for additional scenarios as required. Note: Table E3 and Table E4 do not provide specific sections for aggregation of assessment criteria as this will depend upon the scope of assessment and selected methodology.
Table E4 - Sensitivity Analysis Results
Sensitivity Analysis Scenario | Assessment Criteria Changed | Remediation Options for Assessment |  |  |  |  | Summary of Justification of Revised Scores (refer to Table E3 for more detail)
|  | Option 1 | Option 2 | Option 3 | Option 4 | Option 5
Return to Introduction